## Data
order | section_name | task_label | task_name | start_date | end_date | is_milestone | is_deliverable | done_by | notes
4 | User 2 | api_data_catalogue | API base structure for the data catalogue | after mvp_data_upload | 8w | TRUE |  | rse
4 | User 2 | backend_data_dictionary | Backend structure for storing the data dictionary | after api_data_catalogue | 8w | TRUE |  | dba
4 | User 2 | frontend_data_catalogue | Frontend UI for showing data catalogue | after backend_data_dictionary | 8w | TRUE |  | rse
4 | User 2 | mvp_data_catalogue | MVP of data catalogue | after frontend_data_catalogue | 6w |  | TRUE | rse + dba
4 | User 2 | api_data_request | API base structure for the data selection and request | after api_data_catalogue api_projects | 12w | TRUE |  | rse
4 | User 2 | backend_trigger_data_request_extraction | Backend software for extracting requested data | after api_data_request | 12w | TRUE |  | rse + dba
4 | User 2 | backend_trigger_data_request_transfer | Backend software for transferring data | after backend_trigger_data_request_extraction | 16w | TRUE |  | rse + dba
4 | User 2 | frontend_data_request | Frontend UI for selecting and requesting data | after backend_trigger_data_request_extraction | 8w | TRUE |  | rse
4 | User 2 | mvp_data_request | MVP of data request and transfer | after frontend_data_request | 8w |  | TRUE | rse + dba
4 | User 2 | api_projects | API base structure for projects listings | after api_data_catalogue | 8w | TRUE |  | rse
4 | User 2 | backend_projects | Backend structure for storing project info | after api_projects | 8w | TRUE |  | rse + dba
4 | User 2 | frontend_projects_request_form | Frontend UI for submitting data access request | after backend_projects | 8w | TRUE |  | rse
4 | User 2 | mvp_projects | MVP of projects listings | after backend_projects | 8w |  | TRUE | rse + dba
2 | User 1 | backend_cdm | Backend common data model structure | after pre_hire_staff | 16w | TRUE |  | rse + dba
2 | User 1 | api_routine_data_upload | API base structure for uploading routine data | after backend_cdm | 10w | TRUE |  | rse + dba
2 | User 1 | api_new_data_upload | API base structure for uploading new data | after backend_cdm | 8w | TRUE |  | rse + dba
2 | User 1 | api_trigger_data_cleaning | API trigger for cleaning and processing software | after api_routine_data_upload | 10w | TRUE |  | rse + dba
2 | User 1 | api_trigger_update_changelog | API trigger to updating the changelog and data version | after api_new_data_upload api_routine_data_upload api_trigger_data_cleaning | 8w | TRUE |  | rse
2 | User 1 | backend_changelog | Backend structure for storing the changelog info | after api_trigger_update_changelog | 4w | TRUE |  | rse
2 | User 1 | backend_database | Backend formal structure for storing the final database | after api_trigger_data_cleaning | 16w | TRUE |  | dba
2 | User 1 | backend_dvc | Backend version control structure for data | after backend_changelog backend_database | 16w | TRUE |  | dba
2 | User 1 | frontend_data_upload | Frontend UI for uploading routine or new data | after backend_database | 12w | TRUE |  | rse
2 | User 1 | mvp_data_upload | MVP of data upload | after frontend_data_upload | 8w |  | TRUE | rse + dba
5 | User 3 | api_trigger_format_projects | API trigger for formatting projects into listing | after mvp_data_upload | 8w | TRUE |  | rse
5 | User 3 | api_trigger_format_projects_results | API trigger for formatting project results into listing | after api_trigger_format_projects | 8w | TRUE |  | rse
5 | User 3 | api_trigger_format_changelog | API trigger for formatting changelog into listing | after backend_changelog api_trigger_format_projects | 8w | TRUE |  | rse
5 | User 3 | api_trigger_format_statistics | API trigger for formatting aggregate statistics into listing/images | after backend_database api_trigger_format_projects | 8w | TRUE |  | rse
5 | User 3 | backend_trigger_aggregate_statistics | Backend trigger for generating aggregrate statistics | after api_trigger_format_statistics | 10w | TRUE |  | rse + dba
5 | User 3 | frontend_projects | Frontend UI for list of projects | after api_trigger_format_projects | 4w | TRUE |  | rse
5 | User 3 | frontend_changelog | Frontend UI for listing changelog | after api_trigger_format_changelog | 4w | TRUE |  | rse
5 | User 3 | frontend_statistics | Frontend UI for showing aggregate statistic results and images | after api_trigger_format_statistics | 4w | TRUE |  | rse
5 | User 3 | mvp_projects_list | MVP for listing of projects | after frontend_projects | 8w |  | TRUE | rse
5 | User 3 | mvp_changelog_list | MVP for listing of changelog | after frontend_changelog | 8w |  | TRUE | rse
5 | User 3 | mvp_statistics_list | MVP for listing of aggregate statistics | after frontend_statistics | 8w |  | TRUE | rse
5 | User 3 | u3_continue_dev | Continued development | after mvp_statistics_list | 24w |  |  | rse
3 | User 4 | api_researchers_list | API base structure for list of researchers | after pre_hire_staff | 8w | TRUE |  | rse
3 | User 4 | backend_researchers_list | Backend structure for storing researcher info | after api_researchers_list | 8w | TRUE |  | rse + dba
3 | User 4 | api_trigger_authorization_projects | API trigger for approving projects for data transfer | after backend_projects | 12w | TRUE |  | rse
3 | User 4 | api_trigger_authorization_researchers | API trigger for approving authorization for researchers | after backend_researchers_list | 12w | TRUE |  | rse
3 | User 4 | frontend_admin_projects_list | Frontend UI for listing projects for admin | after mvp_projects | 8w | TRUE |  | rse
3 | User 4 | frontend_admin_researchers_list | Frontend UI for listing researchers for admin | after backend_researchers_list | 8w | TRUE |  | rse
1 | General | pre_hire_staff | Searching for and hiring skilled personnel | 2022-01-01 | 26w | TRUE
1 | General | pre_find_hosting_server | Identify appropriate server for deploying non-personal data and files | 2022-01-01 | 26w | TRUE
1 | General | update_data_dictionary | Mechanism for adding or updating data dictionary and other docs | after mvp_data_catalogue | 8w |  |  | rse
1 | General | pre_find_software | Map all existing software for re-usable components | 2022-01-01 | 52w | TRUE
7 | Training | docs_deploy_framework | Training docs on deploying the framework | after mvp_data_upload | 156w |  |  | rse + dba | These could be deliverables, but for visual, I will not have them be for now.
7 | Training | docs_use_framework | Training docs on using the deployed framework | after mvp_data_upload | 156w |  |  | rse + dba | These could be deliverables, but for visual, I will not have them be for now.
7 | Training | docs_customize_framework | Documentation on customizing the framework | after mvp_data_upload | 156w |  |  | rse + dba | These could be deliverables, but for visual, I will not have them be for now.
7 | Training | docs_contributing | Documentation on maintaining and contributing to the framework | after pre_hire_staff | 156w |  |  | rse + dba | These could be deliverables, but for visual, I will not have them be for now.
7 | Training | docs_usage | Usage docs for each individual component | after pre_hire_staff | 156w |  |  | rse + dba | These could be deliverables, but for visual, I will not have them be for now.
6 | Apply to DD2 | dd2_survey_all_files | Determine location of all DD2 data and plan to link them | after mvp_data_upload | 24w | TRUE
6 | Apply to DD2 | dd2_survey_data_inputs | Determine how and where all data are input from | after mvp_data_upload | 24w | TRUE
6 | Apply to DD2 | dd2_restructure_to_cdm | Move existing DD2 data and restructure to the CDM | after dd2_survey_data_inputs | 24w |  |  | rse + dba
6 | Apply to DD2 | dd2_processing_software | Build DD2 data processing and linking software | after dd2_restructure_to_cdm | 24w | TRUE |  | rse + dba
6 | Apply to DD2 | dd2_implement_framework | Fully implemented in DD2 | after dd2_processing_software | 4w |  | TRUE
|  |  | Replicating in ADDITION cohort | after dd2_implement_framework | 24w

## Metadata
variable_name | description
order | The order for which sections will start first, largely for visual display on the Gantt Chart
section_name | The values in this column are for grouping the Gantt Chart into sections.
task_label | This is a task ID that's used for setting tasks that are dependencies, e.g. in start_date with "after ID".
task_name | This is the text description that will be shown in the Gantt Chart.
start_date | This indicates when the task will start. You can set dependencies like "after ID" or by setting a specific date.
end_date | This is for either how long the task will take (e.g. "24hr" or "3d" or "1y") or is a date for the ending of the task.
is_milestone | This can be used for highlighting the specific tasks as milestones.
is_deliverable | Same as is_milestone, can be used to distinguish deliverable from other tasks.
done_by | Who could build this: dba = database administrator, rse = research software engineer